## Team
Scrum
Member | Role | Email
Jürgen Vogel | Product owner | juergen.vogel@bfh.ch
Raphael Zenhäusern | Scrum master | zenhr1@bfh.ch
Florian Schnyder | Developer | schnf8@bfh.ch
Aline Zaugg | Developer | zauga5@bfh.ch
Dominique Walter | Developer | waltd4@bfh.ch
Philipp Schaad | Developer | schap18@bfh.ch
David Mössner | Developer | mossd1@bfh.ch
Scrum meetings | Time | Room
Wednesday | 16:15 | N421
Thursday | 14:25 | N522
Friday | 14:25 | 308

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login | I want to login as a health visitor | medium (high) | 5h |  |  | working progress
2 | Menu | I want to navigate to another page |  |  |  |  | pending
|  | I need to know which page I am located exactly |  |  |  |  | pending
|  | I want to log out |  |  |  |  | pending
|  | I want to change user settings |  |  |  |  | pending
3 | Home view | My home view shows the three latest newsentries for my clients as well as my next appointment |  |  |  |  | pending
|  | There are news for one of my clients and I want to expand a newsentry to view the full post |  |  |  |  | pending
|  | I want to display the full appointment by clicking onto the next appointment view |  |  |  |  | pending
4 | Agenda | I want to view the full information for any of my appointments in my agenda |  |  |  |  | pending
|  | I need to make a new appointment in my agenda |  |  |  |  | pending
|  | I want to modify an appointment in my agenda |  |  |  |  | pending
|  | I want to delete an appointment in my agenda |  |  |  |  | pending
5 | Clients View | As any user of the app I want to look up a (new) client |  |  |  |  | working progress
|  | I want to see which three recent clients I've looked up |  |  |  |  | pending
6 | Client View / Client Details | I need to know wether my client is classified harmless or not |  |  |  |  | done
|  | primary informations as full name, status and a picture need to be shown at first sight after having selected a client |  |  |  |  | done
|  | I need to know the address of my client |  |  |  |  | done
|  | My client has had an accident, I need to contact his emergency contact |  |  |  |  | done
|  | I have a question about the medication of my client and need to know which is his attending physician. |  |  |  |  | done
|  | My client has moved to another address, as an administrator I need to change the client data |  |  |  |  | working progress
|  | My client has improved, as a doctor I want to change his status to harmless |  |  |  |  | working progress
|  | I need to check the journal entries for a specific client |  |  |  |  | pending
|  | I need to know the medication prescribed for my client |  |  |  |  | pending
7 | Medication | I need to have a list of the drugs currently prescribed to my client |  |  |  |  | pending
|  | My client can't remember wether he has to swallow the small white pill in the morning or as well in the evening. I need to check the prescription |  |  |  |  | pending
|  | My client has drugs without packaging, I need to see a picture of my clients drugs to check wether it is one of the prescribed drugs or not |  |  |  |  | pending
|  | My client needs more drugs, I need to know where he/she usually hands in his/her prescription |  |  |  |  | pending
8 | contacts | I want to call the attending physician of one of my clients, I want to look him/her up in the contact list |  |  |  |  | pending
|  | I want to save a new local contact to my contact list |  |  |  |  | pending
9 | Journal Entry | There are news for one of my clients and I want to post a new journal entry about it |  |  |  |  | pending
|  | I want to modify one of my journal entries |  |  |  |  | pending
|  | I want to delete one of my journal entries |  |  |  |  | pending

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | 1 | Class Structure | Define Packages, Classes & interfaces | Business Logic | schap18,schnf8,zauga5, | high | 2 |  | 2 | done
1.1 | 1 | Class Development | Class Person, Subclass Client,Adress,Doctor | Models | schap18,schnf8,zauga5, | high | 5 |  | 2 | done
1.2 | 1 | Class Development | Class User | Models | mossd1 |  | 1 |  | 1 | done
1.3 | 1 | Class Development | Class Journalentry | Models | mossd1 |  | 3 |  |  | pending
1.4 | 1 | Interface Client | UI Client | Interface | waltd4, zauga5 |  | 10 |  | 19 | working progress
1.5 | 1 | Interface Client | UI Client Data Binding | Interface | schap18, schnf8 |  | 4 |  | 5 | working progress
1.6 | 1 | Client Logic | Develop Business Logic Client | Business Logic | mossd1 |  | 2 |  | 2 | done
1.7 | 1 | Client Data | Develop Data Source Client | Business Logic | zenhr1 |  | 3 |  | 1 | working progress
1.8 | 1 | Login UI | UI Login | Interface | zenhr1 |  | 2 |  | 1 | done
1.9 | 1 | Login Logic | Business Logic Login | Business Logic | zenhr1 |  | 1 |  | 0 | pending
1.10 | 1 | Main UI Class | Main UI Class Structur | Interface | zenhr1 |  | 1 |  | 1 | done
1.11 | 1 | Clients UI | Clients table view with select and search | Interface | zenhr1 |  | 1 |  | 1 | working progress
1.12 | 1 | Clients Logic | Clients search logic | Business Logic | zenhr1 |  | 2 |  |  | pending
2 | 2 | Client UI | Button for: edit, cancel, save, return | Interface | waltd4, zauga5 | high | 1 |  |  | pending
2.1 | 2 | Client UI | Data binding fix | Interface | schap18, schnf8 | high | 2 |  |  | working progress
2.2 | 2 | Journalentry UI | User Interface for Journalentry | Interface | mossd1 | medium | 2 |  |  | pending
2.3 | 2 | Journalentry Logic | Logic for Journalentry | Business Logic | mossd1 | medium | 2 |  |  | pending
2.4 | 2 | Navigation for UI | Menu for Application | Interface | zenhr1 | high | 2 |  |  | pending
2.5 | 2 | Navigation for UI | Menu Logic | Business Logic | zenhr1 | high | 3 |  |  | pending
2.6 | 2 | Client UI | Doctor as Link | Interface | waltd4, zauga5 | low | 1 |  |  | pending
2.7 | 2 | Client UI | Emergency Contact as Link | Interface | waltd4, zauga5 | low | 1 |  |  | pending
2.8 | 2 | Client UI | Windowsize for mobile | Interface | waltd4, zauga5 | high | 2 |  |  | working progress
2.9 | 2 | State Pattern | implementation of state pattern for Menu | Business Logic | ... | ... | ... |  |  | pending

## Burndown Chart
Burndown chart
|  | Burned down |  | Balance |  | Daily Completed
Date | Day | Planned | Actual | Planned | Actual
2014-11-26 | 0 | 0 | 0 | 180 | 180 | 0
| 1 | 0 | 0 | 0 | 180 | 0
| 2 | 0 | 0 | 0 | 180 | 0
| 3 |  |  |  | #N/A | #N/A
| 4 |  |  |  | #N/A | #N/A
| 5 |  |  |  | #N/A | #N/A
| 6 |  |  |  | #N/A | #N/A
| 7 |  |  |  | #N/A | #N/A
| 8 |  |  |  | #N/A | #N/A
| 9 |  |  |  | #N/A | #N/A
| 10 |  |  |  | #N/A | #N/A
| 11 |  |  |  | #N/A | #N/A
| 12 |  |  |  | #N/A | #N/A
| 13 |  |  |  | #N/A | #N/A
| 14 |  |  |  | #N/A | #N/A
| 15 |  |  |  | #N/A | #N/A
| 16 |  |  |  | #N/A | #N/A
| 17 |  |  |  | #N/A | #N/A
| 18 |  |  |  | #N/A | #N/A
| 19 |  |  |  | #N/A | #N/A
| 20 |  |  |  | #N/A | #N/A