## Team
Scrum
Member | Role | Email
Jürgen Vogel | Product owner | juergen.vogel@bfh.ch
Raphael Zenhäusern | Scrum master | zenhr1@bfh.ch
Florian Schnyder | Developer | schnf8@bfh.ch
Aline Zaugg | Developer | zauga5@bfh.ch
Dominique Walter | Developer | waltd4@bfh.ch
Philipp Schaad | Developer | schap18@bfh.ch
David Mössner | Developer | mossd1@bfh.ch
Scrum meetings | Time | Room
Wednesday | 16:15 | N421
Thursday | 14:25 | N522
Friday | 14:25 | 308

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Login process | Login process including verification, authentication and authorization | medium (high) | 5h |  |  | waiting
2 | user administration (CRUD) | Create Read Update Delete system users | medium | 10h |  |  | waiting
3 | permission handling | integradte handling methods for permission levels | low ( high) | 5h |  |  | waiting
4 | CRUD contacts | Create Read Update Delete contacts | medium | 40h |  |  | waiting
5 | show news entrys | displays latest news | low | 10h |  |  | waiting
6 | show client base data | show the clients base data | high | 10h |  |  | waiting
7 | create client | create a new client | medium | 10h |  |  | waiting
8 | CRUD journal entrys | Create Read Update Delete journal entrys | high | 60h |  |  | waiting
9 | drug database | implement the client database | medium | 20h |  |  | waiting
10 | CRUD prescriptions | Create Read Update Delete | medium | 20h |  |  | waiting
11 | CRUD doctor | Create Read Update Delete doctors | medium | 20h |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | 1 | Class Structure | Define Packages, Classes & interfaces | Business Logic | schap18,schnf8,zauga5, | high | 2 |  |  | done
1.1 | 1 | Class Development | Class Person, Subclass Client,Adress,Doctor | Models | schap18,schnf8,zauga5, | high | 5 |  |  | done
1.3 | 1 | Class Development | Class User | Models | mossd1 |  | 3 |  |  | done
1.4 | 1 | Class Development | Class Journalentry | Models |  |  | 3 |  |  | pending
1.5 | 1 | Interface Client | UI Client | Interface | waltd4, zauga5 |  | 10 |  | 15 | working progress
1.6 | 1 | Client | Develop Business Logic Client | Business Logic | mossd1 |  | 2 |  | 2 | done
1.7 | 1 | Client | Develop Data Source Client | Business Logic | zenhr1 |  | 3 |  | 1 | working progress
1.8 | 1 | Login | UI Login | Interface | zenhr1 |  | 2 |  | 1 | done
1.9 | 1 | Login | Business Logic Login | Business Logic | zenhr1 |  | 1 |  | 0 | pending
2 | 1 | Main Class | Main UI Class Structur | Interface | zenhr1 |  | 1 |  | 1 | done

## Burndown Chart
Burndown chart
|  | Burned down |  | Balance |  | Daily Completed
Date | Day | Planned | Actual | Planned | Actual
2014-11-26 | 0 | 0 | 0 | 180 | 180 | 0
| 1 | 0 | 0 | 0 | 180 | 0
| 2 | 0 | 0 | 0 | 180 | 0
| 3 |  |  |  | #N/A | #N/A
| 4 |  |  |  | #N/A | #N/A
| 5 |  |  |  | #N/A | #N/A
| 6 |  |  |  | #N/A | #N/A
| 7 |  |  |  | #N/A | #N/A
| 8 |  |  |  | #N/A | #N/A
| 9 |  |  |  | #N/A | #N/A
| 10 |  |  |  | #N/A | #N/A
| 11 |  |  |  | #N/A | #N/A
| 12 |  |  |  | #N/A | #N/A
| 13 |  |  |  | #N/A | #N/A
| 14 |  |  |  | #N/A | #N/A
| 15 |  |  |  | #N/A | #N/A
| 16 |  |  |  | #N/A | #N/A
| 17 |  |  |  | #N/A | #N/A
| 18 |  |  |  | #N/A | #N/A
| 19 |  |  |  | #N/A | #N/A
| 20 |  |  |  | #N/A | #N/A